## Backlog
Issue No | Tracker | Subject | Description | Status | Priority | Assignee | Start Date | Due Date | Estimated Time | %Done | Parent Task
1 | Sprint | SCRUM Product Backlog | Create a spreadsheet with the tickets for the project. Each ticket is broken down into sub-tickets, until only one definite done criteria is left | In Progress | High | Quoc Khanh Ngo | 2021-03-30 | 2021-04-09 | 1 day | 50 | NULL
2 | Product Backlog | OnkoDICOM Beginning Project | Write a program that open DICOM file. The program will be configurable based on a preferences-configuration record | In Progress | Immediate
| Feature | 1. Config file content | [8 empty] | 2
| Feature | 1.1.User home
| Feature | 1.1.1 Windows | [8 empty] | 3
| Feature | 1.1.2 Mac | [8 empty] | 3
| Feature | 1.1.3 Linux- | [8 empty] | 3
| Feature | 1.2 Hidden directory
| Feature | 1.2.1 Windows
| Feature | 1.2.2 Mac
| Feature | 1.2.3 Linux
| Feature | 1.3 Window/level values
| Feature | 2. SQLite (config file)
| Feature | 2.1 how do access sqlite
| Support | 2.1.1 Training session on SQLite given by Duy Tung Ha | https://www.sqlitetutorial.net/sqlite-python/creating-database/
| Feature | 2.2 How to write to sqlite
| Feature | 2.3 How to read from sqlite
| Feature | 3. Design Application UI (Derived from OnkoDICOM and Dicompyler)
| Feature | 3.1 Welcome Page
| Feature | 3.1.1 Design
| Feature | 3.1.2 Implementation
| Feature | 3.2 Main Page
| Feature | 3.2.1 Design
| Feature | 3.2.2 Implementation
| Feature | 3.3 Image Display
| Feature | 3.3.1 Design
| Feature | 3.3.2 Implementation
| Feature | 4. Open DICOM safe way
| Feature | 4.1 Checking if a DICOM file contains required elements
| Feature | 4.1.1 Defining required elements in DICOM file (done)
| Feature | 4.1.2 Implementation
| Feature | 4.2 Does not contain required elements:
| Feature | 4.2.1 Inform user the missing elements
| Feature | 4.2.2 prompt how to proceed from there (Cancel, Retry)
| Feature | 4.2.3 Execute what user choses (?)
| Feature | 4.3 Open file (when all elements are present)
| Feature | 4.3.1 Exception: File fails to open
| Feature | 4.4 Defining listofAndreworStuart's requirements
| Support | 5. Research
| Support | 5.1 Study DICOM standard | https://dicom.innolitics.com/ciods/rt-dose/rt-dose/3004000a http://dicom.nema.org/medical/dicom/current/output/pdf/
| Support | 5.2 Study pydicom & dicompiler | https://pydicom.github.io/pydicom/stable/old/getting_started.html https://github.com/bastula/dicompyler
| Support | 5.3 Learn PyQT5 | https://youtu.be/Vde5SH8e1OQ?list=PLzMcBGfZo4-lB8MZfHPLTEHO9zJDDLpYj https://www.youtube.com/watch?v=0hN6vSSHT0I
| Support | 6. Git Training
| Support | 6.1 Study version control
| Support | 6.2 Git basic command
| Support | 6.2.1 Commit
| Support | 6.2.2 Push
| Support | 6.2.3 Pull
| Support | 6.2.4 Merge
| Support | 6.3 Collaborating with git
| Support | 6.3.1 Syncing
| Support | 6.3.2 Create pull request
| Support | 6.3.3 Git checkout branches
| Support | 6.3.4 Resolve conflict
| Support | 6.3.4.1 Check conflict on Github
| Support | 6.3.4.2 Use PyCharm Git GUI tool to resolve conflict
| Management | 7. Initial Project Description | A written document outlining the justification for the project with a broad overview and a description of the target audience. This document must include a detailed understanding of the problem and an analysis of current products in the market. It will also outline how the project will be managed and a risk register. This document will have an appendix on the groups ethical and professional approach to the project, along with a group charter. | Closed
| Management | 7.1. Project Scope |  | Closed
| Management | 7.2. Market Analysis |  | Closed
| Management | 7.3. Time Management Plan |  | Closed
| Management | 7.4. Quality Management Plan |  | Closed
| Management | 7.5. Risk Management |  | Closed
| Management | 7.6. Initial Identification of Skills |  | Closed
| Management | 7.7. Appendix |  | Closed
| Management | 7.7.1. Stakeholder Analysis |  | Closed
| Management | 7.7.2. Group Project Charter |  | Closed
| Management | 7.7.3. Group Ethical Approach |  | Closed
| Management | 7.7.4. Meeting Agends and Minutes |  | Closed
| Management | 7.8. Submission Document Finalization