## Product Backlog
ID | Type | Task | Subtask | Definition Problem | Status | Priority | Parent ID
1 | Product Backlog | OnkoDICOM Project |  | Create a program is to be written to open a DICOM file. The program will need to retrieve the DICOM file from a SQLite server. When connecting to the SQLite program, the program will need to check for a configuration file. | New | Immediate
2 |  | Connect to SQLite |  |  |  |  | 1
3 |  | Preferences-Configuration File |  |  |  |  | 1
4 |  |  | Find Preferences-Configuration File |  |  |  | 3
5 |  |  | Read Preferences-Configuration File |  |  |  | 3
6 |  | Preferences |  | The information stored in the configuration file deteremines the path to the default directory containing the DICOM files |  |  | 1
|  |  | Linux | Must be able to navigate in Linux |  |  | 6
8 |  |  | Windows | Must be able to navigate in Windows |  |  | 6
9 |  |  | Mac OS | Must be able to navigate in Mac OS |  |  | 6
10 |  | Open DICOM file |  | Program needs to open DICOM file in a fault tolerant way |  |  | 1
11 |  | Check for Element |  | Program needs to check if element: 'listfromAndreworStuart' is present |  |  | 1
12 |  |  | Find the element |  |  |  | 11
13 |  |  | Ask user input | Program asks for user input if the element does not exist |  |  | 11

## Revised Sheet
Task | Subtask | Subtask | Subtask
PyQt5 - Investigation
Views
Model Class
View Class
Controller Class
Drag and Drop Models
Proxy Models
Model Subclassing
PyQt5 - Learn and Train
Views
Model Class
View Class
Controller Class
Drag and Drop Models
Proxy Models
Model Subclassing
Configuration
SQLite
Home Directory
OnkoDICOM Naming conventions
Python coding standard
PyQt5 MVC Standard
Loading Configuration
SQLite - Investigation
Module
Connection
Cursor
Row
Exceptions
SQL and Python types
Adapters and Converters
Efficient methods
SQLite - Learn and Train
Module
Connection
Cursor Objects
Row Objects
Exceptions
SQL and Python types
Adapters and Converters
Efficient methods
Home Directory - Investigation
Hidden Directory
Windows
Mac
Linux
DICOM Container - Investigation
DICOM-RT
CT
MRI
PET
ListfromAndreworStuart
Design
GUI
UI
Model
Build
Checking Config File
Read Config File
Load Config File
Request Config File
Open DICOM - Fault Tolerant Way
Read DICOM
Check Element
Check if Element Exist
Ask for User Guidance
Verify Element
Read Element Value
Open Image
Display Image
Implementation
View
Controller
Model
Unit Testing
Code
Loading Config File
Connecting to SQLite Database
Directory
Windows
Mac
Linux
Opening DICOM File
Open File
Ask for user guidance
Checking if Element Exist
Read Element
Ask for user guidance
GUI
View Class
UI
Buttons
Textboxes
Evaluation
Requirement Criteria
Refactor
Github
Commit
Pull requqest
Branch
Revision